## Evidence
Your Name | Zheng Zeng
Project Name | StockWatch |  |  | Artifact
Sprint# | Efforts (Hrs) | Towards objectives | Brief Description of Acomplishments | Artifact Name | Location | Reference
Sprint # 1 | 16 | 6[CS, IT] | Wrote tools chain | Powerpoint | Sprint 1.ppt | Page 7
Sprint # 2 | 16 | 6[CS, IT] | Wrote user stories, scenariodefinition and use case | Requirements | User stories.doc | Page 1 to 3
Sprint # 3 | 22 | 6[CS, IT] | Wrote interface optimized code and user stories | Code, Requirements | Stock_web_dic.py/User stories.doc | Page 4
Sprint # 4 | 25 | 6[CS, IT] | Wrote database code, and import data from webpage code | Code | final.py/ create database.doc | All
Sprint # 5 | 24 | 6[CS, IT] | Wrote code to execute/open the python file/picture on the server using the html button. | Code, Powerpoint | stock.html/stock1.html/Sprint 5 | New 12 lines/ 20 lines/ Page 4
Sprint # 6 | 22 | 6[CS, IT] | Wrote code to connect database with frontend/ backend to show the buy and sell graph | Code, Powerpoint | conn.py/show.py | All/ Page 3
Sprint # 7 | 21 | 6[CS, IT] | Wrote code to execute/open the python file form the local using HTML | Code, Powerpoint | test1.py/Sprint7 | All/ Page 4
Sprint # 8
Sprint # 9
Sprint # 10
Sprint # 11
Sprint # 12

## Count
Your Name |  | Zheng Zeng
Project Name |  | StockWatch
Objectives
Sprint# | Team Member | 1 | 2 | 3 | 4 | 5 | 6[CS] | 6[IT]
0 | Zeng, Zheng | 1 | 0 | 1 | 0 | 1 | 0 | 0
1 | Zeng, Zheng | 0 | 0 | 1 | 0 | 1 | 1 | 2
2 | Zeng, Zheng | 2 | 0 | 0 | 1 | 1 | 2 | 3
3 | Zeng, Zheng | 1 | 0 | 1 | 1 | 1 | 2 | 2
4 | Zeng, Zheng | 1 | 1 | 1 | 0 | 1 | 3 | 1
5 | Zeng, Zheng | 1 | 0 | 1 | 1 | 1 | 3 | 1
6 | Zeng, Zheng | 1 | 1 | 1 | 1 | 0 | 2 | 2
7
8